## Cover
Manual Testing Web (eComere) moriitalia.com
Project Name | Functional Testing Web (eCommerce) Moriitalia.com |  |  | Creator | Phan Hoàng Đỉnh
Project Code | Moriitalia.com |  |  | Reviewer/Approver
Document Code |  |  |  | Issue Date | 24/09/2025
Version
Record of change
Change Date | Change Item | Change description | ID Name | Note

## TEST REPORT
TEST REPORT
Project Name | Functional Testing Web (eCommerce) Moriitalia.com |  | Creator |  | Phan Hoàng Đỉnh
Project Code | Moriitalia.com |  | Reviewer/Approver
Document Code |  |  | Issue Date |  | 24/09/2025
Notes
No | Test Items | Pass | Fail | NT | N/A | Number of test cases
1 | Homepage | 12 | 0 | 0 | 0 | 12
2 | User Account
2.1 | Register | 16 | 4 | 4 | 0 | 24
2.2 | Sign-in | 19 | 4 | 0 | 2 | 25
2.3 | Forgot Password | 12 | 0 | 0 | 0 | 12
2.4 | Change Password | 0 | 0 | 22 | 1 | 23
3 | Search Items | 6 | 1 | 10 | 1 | 18
4 | Product Detail | 6 | 6 | 1 | 10 | 23
5 | Shopping Cart | 19 | 6 | 7 | 1 | 33
6 | Payment | 0 | 0 | 0 | 0 | 0
7 | Order Manage | 7 | 2 | 5 | 16 | 30
| Sub total | 97 | 23 | 49 | 31 | 200
| Test coverage |  | 60 | %
| Test successful coverage |  | 80.8333 | %
#REF!
Note on C21: Ongoing.

## TC-Homepage
Item Test | HomePage
Test requirement | Google Chrome Web Browser
Tester | Hoàng Đỉnh
Pass | Fail | NT | N/A | Number of Test cases
12 | 0 | 0 | 0 | 12
% | % | % | %
ID | Test Case Description | Pre-condition | Test Case Procedure | Expected Output | Result | Test date | Tester | Note
UI Testing
[HomePage-1] | _ Perform visual testing of the homepage interface. | _ Visit the URL: Moriitalia.com | _ Reach the page successfully. | _ The homepage interface will present all core features and including the following fields: + Header ( Logo, Navigation Link) + Search Product + Login / Registration + Dropdown list Product Category + Banner Events + Product Image Category + New arrival + Must-Have Household Items + Partner Brands + Footer | Pass | 13/10/2025 | Hoàng Đỉnh
[HomePage-2] | _ Verify Header (Logo, Navigation Link) | _ Visit the URL: Moriitalia.com | _ Reach the page successfully. | _ Display Icon Moriitalia and Navigation Link by default. _ Hover on the icon and navigation link will changes state of cursor. _ Activate the icon will move to homepage, click on navigation link will redirect correct page. | Pass | 13/10/2025 | Hoàng Đỉnh
[HomePage-3] | _ Verify Search Product | _ Visit the URL: Moriitalia.com | _ Input product name "Nồi Cơm" _ Press Enter or click on search icon | _ Display text box, placeholder "Tìm theo tên sản phẩm, thương hiệu," and search icon by default. _ Show dropdown list "Nồi Cơm" when typing and allow user click to access detailed product page. | Pass | 13/10/2025 | Hoàng Đỉnh
[HomePage-4] | _ Verify Login / Registration | _ Visit the URL: Moriitalia.com | _ Hover mouse on Login / Registration area. | _ Display "Đăng Nhập / Đăng Ký" link, icon by default. _ Hover link or icon will show pop-up Login and hide it when the cursor leaves the login area. _ When click on label "Đăng Nhập / Đăng Ký" or login icon, pop-up will show allow user typing email, password to sign-in. | Pass | 13/10/2025 | Hoàng Đỉnh
[HomePage-5] | _ Verify Dropdown list Product Category | _ Visit the URL: Moriitalia.com | _ Reach the page successfully. _ Hover mouse on Dropdown list Product Category area. | _ Display fully 8 columns: "Dụng Cụ Nấu Ăn", "Phụ Kiện Làm Bếp", "Dao - Kéo", "Dụng Cụ Làm Bánh", "Đồ Dùng Bàn Ăn", "Bình Giữ Nhiệt", "Điện Gia Dụng", "Bảo Quản Thực Phẩm", "Quà Tặng". _ Hovering over each category displays the corresponding product list. _ Ensure user can click dropdown list under each product category. | Pass | 13/10/2025 | Hoàng Đỉnh
[HomePage-6] | _ Verify Banner Events | _ Visit the URL: Moriitalia.com | _ Reach the page successfully. | _ Banner events show clearly image with no blur or broken. _ Can navigate button to check previous and next banner. _ Allow user click to see contents on banner. | Pass | 13/10/2025 | Hoàng Đỉnh
[HomePage-7] | _ Verify Product Image Category | _ Visit the URL: Moriitalia.com | _ Reach the page successfully. _ Scrolling down to Product Image Category | _ Display all product by image category. _ Ensure label name as the same with image contents. _ Allow user click to access product category. | Pass | 13/10/2025 | Hoàng Đỉnh
[HomePage-8] | _ Verify New Arrival | _ Visit the URL: Moriitalia.com | _ Reach the page successfully. _ Scrolling down to New Arrival | _ Product show clearly image with no blur or broken. _ Have label name and price under image. _ Can navigate button to check previous and next product. _ Allow user click to see product detail. | Pass | 13/10/2025 | Hoàng Đỉnh
[HomePage-9] | _ Verify Must-Have Household Items | _ Visit the URL: Moriitalia.com | _ Reach the page successfully. _ Scrolling down to Must-Have Household Items | _ Product show clearly image with no blur or broken. _ Have label name and price under image. _ Can navigate button to check previous and next product. _ Allow user click to see product detail. | Pass | 13/10/2025 | Hoàng Đỉnh
[HomePage-10] | _ Verify Partner Brands | _ Visit the URL: Moriitalia.com | _ Reach the page successfully. _ Scrolling down to Partner Brands | _ Label "Moriitalia Luxury" will be highlighted show on page. _ Partner Brands show clearly image with no blur or broken. _ User can press the image brand to see more information. | Pass | 13/10/2025 | Hoàng Đỉnh
[HomePage-11] | _ Verify Footer Link | _ Visit the URL: Moriitalia.com | _ Reach the page successfully. _ Scrolling down to bottom page. | _ System will display link Contact, Customer Support, Career and Social Media icon, Payment icon. _ Verify that the links or Social Media icon will redirect to the intended webpage and no links are broken. | Pass | 13/10/2025 | Hoàng Đỉnh
[HomePage-12] | _ Verify Footer Text | _ Visit the URL: Moriitalia.com | _ Reach the page successfully. _ Scrolling down to bottom page. | _ Footer text area will show correctly: + Company infor (name, founding year, tax code, liscense number). + Hotline and email. + Headquarter, store and factory adress. | Pass | 13/10/2025 | Hoàng Đỉnh

## TC-Register
Item Test | Register
Test requirement | Google Chrome Web Browser
Tester | Hoàng Đỉnh
Pass | Fail | NT | N/A | Number of Test cases
16 | 4 | 4 | 0 | 24
% | % | % | %
ID | Test Case Description | Pre-condition | Test Case Procedure | Expected Output | Result | Test date | Tester | Note
1. UI Testing
[Register-1] | _ Verify UI of Registration | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Đăng Ký". | _ The Registration interface will present the following fields: + Textbox "Họ và Tên", "Email","Điện thoại", "Mậu Khẩu", "Xác Nhận Mật Khẩu". + All related label and placeholder with textbox. + Checkbox "Tôi đã đọc và đồng ý với Chính sách và Qui Định" uncheck by default. + Button "Đăng Ký". | Pass | 13/10/2025 | Hoàng Đỉnh
[Register-2] | _ Verify all Textbox | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Đăng Ký". | _ Text box "Họ và Tên" will show , only allows users to enter up to 30 characters. _ Text box "Email" will show, allow user enter character, number with format user@domain. _ Text box "Điện thoại" will show, only allows users to enter number. _ Text box " Mật Khẩu" will show, character are securely hiden *** when typing. _ Text box " Xác Nhận Mật Khẩu" will show, character are hiden *** when typing. | Pass | 13/10/2025 | Hoàng Đỉnh
[Register-3] | _ Verify Label and Placeholder | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Đăng Ký". | _ All related label and placeholder will show clearly and correct function with textbox content. _ The placeholder will automatically disappear when the user starts typing. | Fail | 13/10/2025 | Hoàng Đỉnh | _ The placeholder is inconsistent with the actual function.
[Register-4] | _ Verify Checkbox | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Đăng Ký". | _ Checkbox will show label "Tôi đã đọc và đồng ý với Chính sách và Quy định" and uncheck by default. _ Allow user enable, disable by click on. _ When the mouse hovers over the checkbox or enable, its border changes color. | Fail | 13/10/2025 | Hoàng Đỉnh | _ Checkbox border not changes color when mouse hover over or enable.
[Register-5] | _ Verify Button "Đăng Ký" | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Đăng Ký". | _ Button "Đăng Ký" will show on page. _ Verify that all button area are clickable, not only text. _ Allow user click on to Registration. _ Hovering over the button triggers a glowing effect that lights up the button. | Pass | 13/10/2025 | Hoàng Đỉnh
2. Functional Testing
[Register-6] | _ Check the registration function | _Visit the URL: Moriitalia.com _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Đăng Ký". | _ At Registration form, leave all fields blank and click on "Đăng Ký" button. | _ System show error message "Vui lòng Đồng Ý Các Điều Khoản" on top page. _ Blank Textbox border will changes to red color and appear label "Vui lòng nhập…" suggestion user enter valid data. _ Registration attempt was not completed. | Pass | 13/10/2025 | Hoàng Đỉnh
[Register-7] |  | _Visit the URL: Moriitalia.com _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Đăng Ký". | _ Enter valid data to all fields. _ Click on "Đăng Ký" button. | _ User registration session completed, redirecting to homepage. _ A confirmation email will be sent to user address after successful registration. _ Label "Đăng Nhập / Đăng Ký" on top page will be replaced by user name. | Pass | 13/10/2025 | Hoàng Đỉnh
[Register-8] |  | _Visit the URL: Moriitalia.com _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Đăng Ký". | _ Enter incorrect format by not following "username@domain.extension" in email field. _ Enter valid data to in the remaining fields. _ Click on "Đăng Ký" button. | _ Label "Địa chỉ email không hợp lệ " will appear under email when typing on the field. _ Registration attempt was not completed. | Pass | 13/10/2025 | Hoàng Đỉnh
[Register-9] |  | _Visit the URL: Moriitalia.com _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Đăng Ký". | _ Enter an already existing email address with '+1' added, following the format: userexisted1@domain.extension _ Enter valid data to in the remaining fields. _ Click on "Đăng Ký" button. | _ Label "Địa chỉ email này đã được sử dụng. Vui lòng đăng nhập hoặc chọn chức năng Quên Mật Khẩu " will appear under email when typing on the field. _ Registration attempt was not completed. | Fail | 13/10/2025 | Hoàng Đỉnh | _ Allow user created account via email address with +1 add: userexisted+1@domain.extension.
[Register-10] |  | _Visit the URL: Moriitalia.com _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Đăng Ký". | _ Enter number and character in phone field. _ Enter valid data to in the remaining fields. _ Click on "Đăng Ký" button. | _ Label "Số điện thoại không chính xác " will appear under Phone field. _ Registration attempt was not completed. | Pass | 13/10/2025 | Hoàng Đỉnh
[Register-11] |  | _Visit the URL: Moriitalia.com _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Đăng Ký". | _ Enter only 3 character in password, enter valid data to in the remaining fields. _ Click on "Đăng Ký" button. | _ Label "Mật khẩu phải có 4 ký tự bao gồm chữ và số " will appear under password field. _ Registration attempt was not completed. | Pass | 13/10/2025 | Hoàng Đỉnh
[Register-12] |  | _Visit the URL: Moriitalia.com _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Đăng Ký". | _ Enter only 4 character in password. _ Enter valid data to in the remaining fields. _ Click on "Đăng Ký" button. | _ Label "Mật khẩu phải có 4 ký tự bao gồm chữ và số " will appear under password field. _ Registration attempt was not completed. | Pass | 13/10/2025 | Hoàng Đỉnh
[Register-13] |  | _Visit the URL: Moriitalia.com _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Đăng Ký". | _ Enter only 3 number in password, enter valid data to in the remaining fields. _ Click on "Đăng Ký" button. | _ Label "Mật khẩu phải có 4 ký tự bao gồm chữ và số " will appear under password field. _ Registration attempt was not completed. | Pass | 13/10/2025 | Hoàng Đỉnh
[Register-14] |  | _Visit the URL: Moriitalia.com _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Đăng Ký". | _ Enter only 4 number in password, enter valid data to in the remaining fields. _ Click on "Đăng Ký" button. | _ Label "Mật khẩu phải có 4 ký tự bao gồm chữ và số " will appear under password field. _ Registration attempt was not completed. | Pass | 13/10/2025 | Hoàng Đỉnh
[Register-15] |  | _Visit the URL: Moriitalia.com _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Đăng Ký". | _ Enter 4 characters including both character and numbers, with a space " " at the end. _ Enter valid data to in the remaining fields. _ Click on "Đăng Ký" button. | _ Label "Mật khẩu không được có khoảng trắng" will appear under password field. _ Registration attempt was not completed. | Fail | 13/10/2025 | Hoàng Đỉnh | _ Spaces are allowed in the password field.
[Register-16] |  | _Visit the URL: Moriitalia.com _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Đăng Ký". | _ Enter Password confirmation does not match with Password. _ Enter valid data to in the remaining fields. _ Click on "Đăng Ký" button. | _ Label "Mật khẩu và mật khẩu xác nhận không giống nhau. " will appear under password field. _ Registration attempt was not completed. | Pass | 13/10/2025 | Hoàng Đỉnh
[Register-17] |  | _Visit the URL: Moriitalia.com _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Đăng Ký". | _ Navigate or access each fields on Register form by presssing the "Tab" on the keyboard. | _ Each field on Register form will be selected when pressing the "Tab" keyboard. | Pass | 13/10/2025 | Hoàng Đỉnh
[Register-18] |  | _Visit the URL: Moriitalia.com _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Đăng Ký". | _ Attempt to register using an email address that has already been registered. _ Enter valid data to in the remaining fields. _ Click on "Đăng Ký" button. | _ System will show "Địa chỉ email này đã được sử dụng. Vui lòng đăng nhập hoặc chọn chức năng Quên Mật Khẩu." _ Registration attempt was not completed. | Pass | 13/10/2025 | Hoàng Đỉnh
[Register-19] |  | _Visit the URL: Moriitalia.com _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Đăng Ký". | _ Activate the Google social icon link to enable sign-up. | _ Redirect to sign-in with google page. _ Allow login via api and return homepage. _ Ensure user using both email and social platform with the same email. It will be treated as a single account, not two separate ones. | Pass | 13/10/2025 | Hoàng Đỉnh
[Register-20] |  | _Visit the URL: Moriitalia.com _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Đăng Ký". | _ Enter valid data to all fields. _ Click on "Đăng Ký" button. _ Login email address has been registered. _ Access the inbox mail, find the verification email. | _ The confirmation email was sent from the correct address. _ The email will be sending to the inbox folder, not the spam folder. _ Email content are in the correct format. | Pass | 13/10/2025 | Hoàng Đỉnh
3. Database Testing
[Register-21] | _ Verify the data stored in the database. | _ Authorized to access the database server. _ User has been added. | _ Check for duplicate records: SELECT COUNT(*) FROM users WHERE email = 'user1@example.com'; | _ Return 1 result. | Untested
[Register-22] |  | _ Authorized to access the database server. _ User has been added. | _Validate email format: SELECT email FROM users WHERE email NOT LIKE '%@%.%'; | _ No result should be returned. | Untested
[Register-23] |  | _ Authorized to access the database server. _ User has been added. | _ Verify that the password is encrypted: SELECT password FROM users WHERE email = 'user1@example.com'; | _ Password should be in hashed format (not plain text) | Untested
[Register-24] |  | _ Authorized to access the database server. _ User has been added. | _ Check user role: SELECT role FROM users WHERE email = 'user1@example.com'; | _ Value should be returned user member, etc. | Untested

## TC-Sign-in
Item Test | Sign-in
Test requirement | Google Chrome Web Browser
Tester | Hoàng Đỉnh
Pass | Fail | NT | N/A | Number of Test cases
19 | 4 | 0 | 2 | 25
% | % | % | %
ID | Test Case Description | Pre-condition | Test Case Procedure | Expected Output | Result | Test date | Tester | Note
1. UI Testing
[Sign-in-1] | _ Verify UI of Sign-in. | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. | _ The Login interface wil popup and present the following fields: + Textbox "Nhập Email", "Nhập Mật Khẩu". + Show Hide password eye icon 👁️ + Forgot Password Link "Quên Mật Khẩu". + Registration Link "Đăng Ký". + Button "Đăng Nhập". + Checkbox "Ghi Nhớ Thông Tin Đăng Nhập" + Social platform login icon. | Fail |  | Hoàng Đỉnh
[Sign-in-2] | _ Verify Textbox "Nhập Email", "Nhập Mật Khẩu". | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. | _ System will display blank Textbox with placeholder "Nhập Email", "Nhập Mật Khẩu" by default. _ The placeholder will automatically disappear when the user starts typing. _ Allow user input up to 50 character in textbox "Nhập Email". _ Allow user input up to 20 character and securely hiden *** when typing. _ Label "Nhập Email*:", "Nhập Mật Khẩu" will align correctly with textbox. | Pass
[Sign-in-3] | _ Verify Show Hide password icon | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. | _ Show Hide password eye icon 👁️ will display on page and hiden password by default. _ User able to show or hide password by activate / inactivate icon. | N/A |  |  | _ Show / Hide password icon not available.
[Sign-in-4] | _ Verify Forgot Password link | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. | _ Forgot Password Link "Quên Mật Khẩu ?" will display on page by default. _ Hovering over link will trigger a glowing effect. _ User able to click link will redirect to Forgot Password page. | Pass
[Sign-in-5] | _ Verify Registration link | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. | _ Forgot Password Link "Quên Mật Khẩu ?" will display on page by default. _ Hovering over link will trigger a glowing effect. _ User able to click link will redirect to Registration Password page. | Pass
[Sign-in-6] | _ Verify Button "Đăng Nhập" | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. | _ Button "Đăng Nhập" will show on page. _ Verify that all button area are clickable, not only text. _ Allow user click on to login. _ Hovering over the button triggers a glowing effect that lights up the button. | Pass
[Sign-in-7] | _ Verify Checkbox "Ghi nhớ thông tin đăng nhập" | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. | _ Checkbox will show label "Ghi nhớ thông tin đăng nhập" and uncheck by default. _ Allow user enable, disable by click on. _ When the mouse hovers over the checkbox, its border changes color. | N/A |  |  | _ Checkbox "Ghi nhớ thông tin đăng nhập" not available.
[Sign-in-8] | _ Verify Social platform login icon | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. | _ The system displays three social login options: Facebook, Google, and Microsoft. _When a user clicks on a social login icon, the corresponding platform's authentication API is activate. | Pass
2. Functional Testing
[Sign-in-9] | _ Check Sign-in Functional | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Login attempt using account created successfully. _ Press the button "Đăng Nhập". | _ User login successfully and redirect to homepage. _ Label "Đăng Nhập / Đăng Ký" on top page will be replaced by user name. | Pass
[Sign-in-10] |  | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Enter valid data to textbox "Nhập Email", "Nhập Mật Khẩu". _ Pressing the "Enter" on the keyboard | _ User login successfully and redirect to homepage. _ Label "Đăng Nhập / Đăng Ký" on top page will be replaced by user name. | Pass
[Sign-in-11] |  | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on icon Google api login. | _ A new browser tab opens, redirecting to the "Sign in with Google" page. _ After user successfully authenticates on google page, user is redirected back to the homepage with logged-in status. | Pass
[Sign-in-12] |  | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on icon Facebook api login. | _ A new browser tab opens, redirecting to the "Log in to Facebook" page. _ After user successfully authenticates on facebook page, user is redirected back to the homepage with logged-in status. | Pass
[Sign-in-13] |  | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on icon Microsoft api login. | _ A new browser tab opens, redirecting to the "Sign in" page. _ After user successfully authenticates on microsoft page, user is redirected back to the homepage with logged-in status. | Pass
[Sign-in-14] |  | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Enter valid data to textbox "Nhập Email", "Nhập Mật Khẩu". _ Activate checkbox "Ghi nhớ thông tin đăng nhập". _ Reload page, return sing-in form again. | _ User's login information remains in the input fields. | Fail |  |  | _ Checkbox "Ghi nhớ thông tin đăng nhập" not available.
[Sign-in-15] |  | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Login attempt using account created successfully. _ Press the button "Đăng Nhập". _ Pressing the reload or back button on web browser. | _ User is not sign-out remaining logged status. | Pass
[Sign-in-16] |  | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Login attempt using account created successfully. _ Press the button "Đăng Nhập". _ Do not perform any actions during the configured timeout period (test 60 minute). _ Pressing the reload or back button on web browser. | _ Redirect the user to the login screen or display a message prompting re-authentication. _ Required re-authentication to access user functional. | Fail |  |  | _ System not show message and required user re-authentication.
[Sign-in-17] |  | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Attempt (test 5 times) sign-in using incorrect password in existed account. _ Press the button "Đăng Nhập". | _The system will show ""Bạn đã nhập sai mật khẩu 5 lần. Vui lòng thử lại sau 10 phút.". _ Temporarily lock access and require a 10-minute waiting period before allowing further login attempts. | Fail |  |  | _ System does not show an error message and locks access after 5 sign-in attempts with an incorrect password.
[Sign-in-18] |  | _Visit the URL: Moriitalia.com | _ Navigate or access each fields on Sign-in form by presssing the "Tab" on the keyboard. | _ Each field on Sign-in form will be selected when pressing the "Tab" keyboard. | Pass
[Sign-in-19] |  | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Leave the textbox "Nhập Email", "Nhập Mẩu Khẩu" blank. _ Press the button "Đăng Nhập". | _ Sign-in form will show message "Vui lòng nhập Email" under textbox "Nhập Email". _ Sign-in attempt was not completed. | Pass
[Sign-in-20] |  | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Enter valid data to textbox "Nhập Email". _ Leave textbox "Nhập Mẩu Khẩu" blank. _ Press the button "Đăng Nhập". | _ System will redirect to login page. _ Sign-in form will show message "Vui lòng nhập Mật Khẩu" under textbox "Nhập Mật Khẩul". _ Sign-in attempt was not completed. | Pass
[Sign-in-21] |  | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Enter valid data to textbox "Nhập Mật Khẩu". _ Leave textbox "Nhập Email" blank. _ Press the button "Đăng Nhập". | _ Sign-in form will show message "Vui lòng nhập Email" under textbox "Nhập Email". _ Sign-in attempt was not completed. | Pass
[Sign-in-22] |  | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Enter invalid data without symbol "@" in textbox "Nhập Email" ("usernamedomain.extension") | _ Label "Địa chỉ email không hợp lệ " will appear under email field. | Pass
[Sign-in-23] |  | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Enter invalid data without symbol "." in textbox "Nhập Email". ("username@domainextension") | _ Label "Địa chỉ email không hợp lệ " will appear under email field. | Pass
[Sign-in-24] |  | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Enter valid data in textbox "Nhập Email" with a space " " at the end. | _ When the user enters an email with extra spaces, the system trims the spaces. _ No error message is displayed. | Pass
[Sign-in-25] |  | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Enter valid data to textbox "Nhập Email". _ Enter invalid data to textbox "Nhập Mật Khẩu". _ Press the button "Đăng Nhập". | _ System will redirect to login page. _ Email information remains in the input fields. _ Sign-in form will show message "Đăng nhập không thành công vui lòng thử lại". _ Sign-in attempt was not completed. | Pass

## TC-Forgot Password
Item Test | Forgot Password
Test requirement | Google Chrome Web Browser
Tester | Hoàng Đỉnh
Pass | Fail | NT | N/A | Number of Test cases
12 | 0 | 0 | 0 | 12
% | % | % | %
ID | Test Case Description | Pre-condition | Test Case Procedure | Expected Output | Result | Test date | Tester | Note
1. UI Testing
[Forgot Password-1] | _ Verify UI of Forgot Password. | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Quên Mật Khẩu". | _ The Forgot Password interface wil present the following fields: + Title "Quên Mật Khẩu". + Label "Vui lòng cung cấp email đã đăng ký để lấy lại mật khẩu.", + Textbox "Email" + Button "Gửi" | Pass
[Forgot Password-2] | _ Verify Title "Quên Mật Khẩu" | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Quên Mật Khẩu". | _ System will display title "Quên mật khẩu". _ The title should not be cut off, overflow, and align left. | Pass
[Forgot Password-3] | _ Verify Label "Vui lòng cung cấp email đã đăng ký để lấy lại mật khẩu." | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Quên Mật Khẩu". | _ Show label "Vui lòng cung cấp email đã đăng ký để lấy lại mật khẩu." by default. | Pass
[Forgot Password-4] | _ Verify Textbox "Email" | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Quên Mật Khẩu". | _ System will display blank Textbox with placeholder "Nhập Email đã đăng ký" by default. _ Label "Email*:" will align correctly with textbox. _ The placeholder will automatically disappear when the user starts typing. | Pass
[Forgot Password-5] | _ Verify Button "Gửi" | _Visit the URL: Moriitalia.com | _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Quên Mật Khẩu". | _ Button "Gửi" will show on page. _ Verify that all button area are clickable, not only text. _ Allow user click on to send email. _ Hovering over the button triggers a glowing effect that lights up the button. | Pass
2. Functional Testing
[Forgot Password-6] | _ Check Forgot Password functional | _Visit the URL: Moriitalia.com _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Quên Mật Khẩu". | _ Enter valid data to textbox "Email:*". _ Pressing the button "Gửi". | _ System wil appear label "Email đã được gửi, vui long kiểm tra hộp thư của bạn." _ A request change password email will be sent to correct address. | Pass
[Forgot Password-7] |  | _Visit the URL: Moriitalia.com _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Quên Mật Khẩu". | _ Enter a non-existent email address into the "Email" field. _ Pressing the button "Gửi". | _ System wil appear label "Không tìm thấy địa chỉ Email." _ Send mail attempt was not completed. | Pass
[Forgot Password-8] |  | _Visit the URL: Moriitalia.com _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Quên Mật Khẩu". | _ Leave field "Email" blank. _ Pressing the button "Gửi". | _ System wil appear label "Vui lòng nhập email." _ Send mail attempt was not completed. | Pass
[Forgot Password-9] |  | _Visit the URL: Moriitalia.com _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Quên Mật Khẩu". | _ Enter valid data to textbox "Email:*". _ Pressing the button "Gửi". _ Do not click the confỉmation link in the email within 24 hours. _ Login email address has been registered. _ Access the inbox mail, click authentication link in the verification email. | _ System wil appear message "Đường dẫn khôi phục mật khẩu của bạn đã hết hạn." | Pass
[Forgot Password-10] |  | _Visit the URL: Moriitalia.com _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Quên Mật Khẩu". | _ Enter valid data to textbox "Email:*". _ Pressing the button "Gửi". _ Login email address has been registered. _ Access the inbox mail, find the verification email. | _ The confirmation email was sent from the correct address. _ Request change password mail show subject "[Moriitalia] - Yêu cầu thay đổi mật khẩu". _ The email will be sending to the inbox folder, not the spam folder. _ Email content are in the correct format. | Pass
[Forgot Password-11] |  | _Visit the URL: Moriitalia.com _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Quên Mật Khẩu". | _ Enter valid data to textbox "Email:*". _ Pressing the button "Gửi". _ Login email address has been registered. _ Access the inbox mail, click authentication link in the verification email. | _ User redirect to Change Password page in web. | Pass
[Forgot Password-12] |  | _Visit the URL: Moriitalia.com _ Mouse hover on "Đăng Nhập / Đăng Ký" label or icon. _ Click on internal link "Quên Mật Khẩu". | _ Enter valid data to textbox "Email:*". _ Pressing the button "Gửi". _ Login email address has been registered. _ Access the inbox mail, click authentication link in the verification email. | _ The content of the email follows the correct format as specified in the technical documentation. | Pass

## TC-Change Password
Item Test | Change Password
Test requirement | Google Chrome Web Browser
Tester | Hoàng Đỉnh
Pass | Fail | NT | N/A | Number of Test cases
0 | 0 | 22 | 1 | 23
% | % | % | %
ID | Test Case Description | Pre-condition | Test Case Procedure | Expected Output | Result | Test date | Tester | Note
1. UI Testing
[Change Password-1] | _ Verify UI of Change Password. | _ Visit the URL: Moriitalia.com _ The user successfully sign-in into the system. | _ Mouse hover on "User Name" label or icon. _ Click on the dropdown link "Thông tin của tôi" and select "Đổi Mật Khẩu". | _ The Forgot Password interface wil present the following fields: + Title "Đổi Mật Khẩu". + Textbox "Mật khẩu cũ" + Textbox "Mẩu khẩu mới" + Textbox "Xác nhận lại mật khẩu" + Label "Độ Mạnh Mật Khẩu" + Button "ĐỔI MẬT KHẨU" | Untested
[Change Password-2] | _ Verify title "Đổi Mật Khẩu" | _ Visit the URL: Moriitalia.com _ The user successfully sign-in into the system. | _ Mouse hover on "User Name" label or icon. _ Click on the dropdown link "Thông tin của tôi" and select "Đổi Mật Khẩu". | _ System will display title "Quên mật khẩu". _ The title should not be cut off, overflow, and align left. | Untested
[Change Password-3] | _ Verify textbox "Mật khẩu cũ" | _ Visit the URL: Moriitalia.com _ The user successfully sign-in into the system. | _ Mouse hover on "User Name" label or icon. _ Click on the dropdown link "Thông tin của tôi" and select "Đổi Mật Khẩu". | _ System will display blank Textbox with placeholder " Nhập mật khẩu cũ" by default. _ Label "Mật khẩu cũ*:" will align correctly with textbox. _ Allow user input up to 20 character in textbox. _ The placeholder will automatically disappear and character are securely hiden *** when the user starts typing. | Untested
[Change Password-4] | _ Verify textbox "Mật khẩu mới" | _ Visit the URL: Moriitalia.com _ The user successfully sign-in into the system. | _ Mouse hover on "User Name" label or icon. _ Click on the dropdown link "Thông tin của tôi" and select "Đổi Mật Khẩu". | _ System will display blank Textbox with placeholder "Mật khẩu ít nhất 4 ký tự bao gồm chữ và số" by default. _ Label "Mật khẩu mới*:" will align correctly with textbox. _ Allow user input up to 20 character in textbox. _ The placeholder will automatically disappear and character are securely hiden *** when the user starts typing. | Untested
[Change Password-5] | _ Verify "Xác nhận lại mật khẩu". | _ Visit the URL: Moriitalia.com _ The user successfully sign-in into the system. | _ Mouse hover on "User Name" label or icon. _ Click on the dropdown link "Thông tin của tôi" and select "Đổi Mật Khẩu". | _ System will display blank Textbox with placeholder " Nhập lại mật khẩu" by default. _ Label "Xác nhận lại mật khẩu" will align correctly with textbox. _ Allow user input up to 20 character in textbox. _ The placeholder will automatically disappear and character are securely hiden *** when the user starts typing. | Untested
[Change Password-6] | _ Verify label "Độ mạnh mật khẩu" | _ Visit the URL: Moriitalia.com _ The user successfully sign-in into the system. | _ Mouse hover on "User Name" label or icon. _ Click on the dropdown link "Thông tin của tôi" and select "Đổi Mật Khẩu". | _ Either the "Mật Khẩu Cũ" or "Mật Khẩu Mới" field should be displayed password strength (e.g., "Yếu", "Trung Bình", "Mạnh") when user enter the password. | N/A
[Change Password-7] | _ Button "ĐỔI MẬT KHẨU" | _ Visit the URL: Moriitalia.com _ The user successfully sign-in into the system. | _ Mouse hover on "User Name" label or icon. _ Click on the dropdown link "Thông tin của tôi" and select "Đổi Mật Khẩu". | _ Button "ĐỔI MẬT KHẨU" will show on page. _ Verify that all button area are clickable, not only text. _ Allow user press to change password. _ Hovering over the button triggers a glowing effect that lights up the button. | Untested
2. Functional Testing
***Note: User's current password = Test@123
[Change Password-8] | _ Check Change Password functional | _ The user successfully sign-in into the system. Hover over the "User Name" label or icon → open the "Thông tin của tôi" dropdown → select the "Đổi Mật Khẩu" form. | _ Navigate or access each fields on "Đổi Mật Khẩu" form by presssing the "Tab" on the keyboard. | _ Each field on "Đổi Mật Khẩu" form will be selected when pressing the "Tab" keyboard. | Untested
[Change Password-9] |  | _ The user successfully sign-in into the system. Hover over the "User Name" label or icon → open the "Thông tin của tôi" dropdown → select the "Đổi Mật Khẩu" form. | Fill in all three password fields: +Mật khẩu cũ: Test@123 +Mẩu khẩu mới: Testing@123 +Xác nhận lại mật khẩu: Testing@123 _ Pressing the "Enter" on the keyboard | _ Label "Mật khẩu đã được thay đổi." will appear on Đổi mật khẩu form. _ User change password session completed. | Untested
[Change Password-10] |  | _ The user successfully sign-in into the system. Hover over the "User Name" label or icon → open the "Thông tin của tôi" dropdown → select the "Đổi Mật Khẩu" form. | Fill in all three password fields: +Mật khẩu cũ: Test@123 +Mẩu khẩu mới: Testing@123 +Xác nhận lại mật khẩu: Testing@123 _ Pressing the button "Đổi Mật Khẩu". _ Log-out -> log-in to the website using the newly updated password. | _ User login successfully and redirect to homepage. | Untested
[Change Password-11] |  | _ The user successfully sign-in into the system. Hover over the "User Name" label or icon → open the "Thông tin của tôi" dropdown → select the "Đổi Mật Khẩu" form. | Fill in all three password fields: +Mật khẩu cũ: Test@123 +Mẩu khẩu mới: aaaaabbbbbccccc12345 (max 20) +Xác nhận lại mật khẩu: aaaaabbbbbccccc12345 _ Pressing the button "Đổi Mật Khẩu". | _ Label "Mật khẩu đã được thay đổi." will appear on Đổi mật khẩu form. _ User change password session completed. | Untested
[Change Password-12] |  | _ The user successfully sign-in into the system. Hover over the "User Name" label or icon → open the "Thông tin của tôi" dropdown → select the "Đổi Mật Khẩu" form. | Fill in all three password fields: +Mật khẩu cũ: Test@123 +Mẩu khẩu mới: aaaaabbbbbccccc123456 (length 21) +Xác nhận lại mật khẩu: aaaaabbbbbccccc123456 _ Pressing the button "Đổi Mật Khẩu". | _ Label "Mật khẩu phải có ít nhất 4 đến 20 ký tự bao gồm chữ và số." will appear on Đổi mật khẩu form. _ Change password attempt was not completed.
[Change Password-13] |  | _ The user successfully sign-in into the system. Hover over the "User Name" label or icon → open the "Thông tin của tôi" dropdown → select the "Đổi Mật Khẩu" form. | Fill in all three password fields: +Mật khẩu cũ: Test@123 +Mẩu khẩu mới: abc1 (min 4) +Xác nhận lại mật khẩu: abc1 _ Pressing the button "Đổi Mật Khẩu". | _ Label "Mật khẩu đã được thay đổi." will appear on Đổi mật khẩu form. _ User change password session completed.
[Change Password-14] |  | _ The user successfully sign-in into the system. Hover over the "User Name" label or icon → open the "Thông tin của tôi" dropdown → select the "Đổi Mật Khẩu" form. | Fill in all three password fields: +Mật khẩu cũ: Test@123 +Mẩu khẩu mới: ab3 (length 3) +Xác nhận lại mật khẩu: ab3 _ Pressing the button "Đổi Mật Khẩu". | _ Label "Mật khẩu phải có ít nhất 4 đến 20 ký tự bao gồm chữ và số." will appear on Đổi mật khẩu form. _ Change password attempt was not completed.
[Change Password-15] |  | _ The user successfully sign-in into the system. Hover over the "User Name" label or icon → open the "Thông tin của tôi" dropdown → select the "Đổi Mật Khẩu" form. | Fill in all three password fields: +Mật khẩu cũ: Test@123 +Mẩu khẩu mới: Test@123 +Xác nhận lại mật khẩu: Test@123 _ Pressing the button "Đổi Mật Khẩu". | _ Label "Mật khẩu của bạn trùng với mật khẩu gần nhất bạn sử dụng. Vui lòng chọn mật khẩu khác." will appear on Đổi mật khẩu form. _ Change password attempt was not completed. | Untested
[Change Password-16] |  | _ The user successfully sign-in into the system. Hover over the "User Name" label or icon → open the "Thông tin của tôi" dropdown → select the "Đổi Mật Khẩu" form. | Fill in all three password fields: +Mật khẩu cũ: Test@123 +Mẩu khẩu mới: Testabcd (all character) +Xác nhận lại mật khẩu: Testabcd _ Pressing the button "Đổi Mật Khẩu". | _ Label "Mật khẩu phải có ít nhất 4 đến 20 ký tự bao gồm chữ và số." will appear on Đổi mật khẩu form. _ Change password attempt was not completed. | Untested
[Change Password-17] |  | _ The user successfully sign-in into the system. Hover over the "User Name" label or icon → open the "Thông tin của tôi" dropdown → select the "Đổi Mật Khẩu" form. | Fill in all three password fields: +Mật khẩu cũ: Test@123 +Mẩu khẩu mới: 123456789 (all number) +Xác nhận lại mật khẩu: 123456789 _ Pressing the button "Đổi Mật Khẩu". | _ Label "Mật khẩu phải có ít nhất 4 đến 20 ký tự bao gồm chữ và số." will appear on Đổi mật khẩu form. _ Change password attempt was not completed. | Untested
[Change Password-18] |  | _ The user successfully sign-in into the system. Hover over the "User Name" label or icon → open the "Thông tin của tôi" dropdown → select the "Đổi Mật Khẩu" form. | Fill in all three password fields: +Mật khẩu cũ: Test@123 +Mẩu khẩu mới: abcd#$%& (special character) +Xác nhận lại mật khẩu: abcd#$%& _ Pressing the button "Đổi Mật Khẩu". | _ Label "Mật khẩu không được phép có ký tự đặc biệt chi bao gồm chữ và số." will appear on Đổi mật khẩu form. _ Change password attempt was not completed. | Untested
[Change Password-19] |  | _ The user successfully sign-in into the system. Hover over the "User Name" label or icon → open the "Thông tin của tôi" dropdown → select the "Đổi Mật Khẩu" form. | Fill in all three password fields: +Mật khẩu cũ: Test@123 +Mẩu khẩu mới: Xyz@1234 +Xác nhận lại mật khẩu: Abc@1234 _ Pressing the button "Đổi Mật Khẩu". | _ Label "Mật khẩu mới và mật khẩu xác nhận không giống nhau." will appear on Đổi mật khẩu form. _ Change password attempt was not completed. | Untested
[Change Password-20] |  | _ The user successfully sign-in into the system. Hover over the "User Name" label or icon → open the "Thông tin của tôi" dropdown → select the "Đổi Mật Khẩu" form. | Fill in all three password fields: +Mật khẩu cũ: Test@123 +Mẩu khẩu mới: Abcd@123 +Xác nhận lại mật khẩu: abcd@123 _ Pressing the button "Đổi Mật Khẩu". | _ Label "Mật khẩu mới và mật khẩu xác nhận không giống nhau." will appear on Đổi mật khẩu form. _ Change password attempt was not completed. | Untested
[Change Password-21] |  | _ The user successfully sign-in into the system. Hover over the "User Name" label or icon → open the "Thông tin của tôi" dropdown → select the "Đổi Mật Khẩu" form. | Fill in all three password fields: +Mật khẩu cũ: Demo@123 (non validation) +Mẩu khẩu mới: ABCD@123 +Xác nhận lại mật khẩu: ABCD@123 _ Pressing the button "Đổi Mật Khẩu". | _ Label "Mật khẩu cũ không hợp lệ" will appear on Đổi mật khẩu form. _ Change password attempt was not completed. | Untested
[Change Password-22] |  | _ The user successfully sign-in into the system. Hover over the "User Name" label or icon → open the "Thông tin của tôi" dropdown → select the "Đổi Mật Khẩu" form. | Fill in all three password fields: +Mật khẩu cũ: "" +Mẩu khẩu mới: "" +Xác nhận lại mật khẩu: "" _ Pressing the button "Đổi Mật Khẩu". | _ Label "Vui lòng nhập..." will appear all three password fields on "Đổi mật khẩu" form. _ Change password attempt was not completed. | Untested
[Change Password-23] |  | _ The user successfully sign-in into the system. Hover over the "User Name" label or icon → open the "Thông tin của tôi" dropdown → select the "Đổi Mật Khẩu" form. | Fill in all three password fields: +Mật khẩu cũ: Test@123 +Mẩu khẩu mới: "" +Xác nhận lại mật khẩu: "" _ Pressing the button "Đổi Mật Khẩu". | _ Label "Vui lòng nhập..." will appear on "Mật khẩu mới", "Xác nhận mật khẩu mới". _ Change password attempt was not completed. | Untested
[Change Password-24] |  | _ The user successfully sign-in into the system. Hover over the "User Name" label or icon → open the "Thông tin của tôi" dropdown → select the "Đổi Mật Khẩu" form. | Fill in all three password fields: +Mật khẩu cũ: "" +Mẩu khẩu mới: "" +Xác nhận lại mật khẩu: Test@123 _ Pressing the button "Đổi Mật Khẩu". | _ Label "Vui lòng nhập..." will appear on "Mật khẩu cũ", "Mật khẩu mới". _ Change password attempt was not completed. | Untested
[Change Password-25] |  | _ The user successfully sign-in into the system. Hover over the "User Name" label or icon → open the "Thông tin của tôi" dropdown → select the "Đổi Mật Khẩu" form. | Fill in all three password fields: +Mật khẩu cũ: Test@123 +Mẩu khẩu mới: Abcd@123 +Xác nhận lại mật khẩu: "" _ Pressing the button "Đổi Mật Khẩu". | _ Label "Vui lòng nhập..." will appear on "Xác nhận lại mật khẩu". _ Change password attempt was not completed. | Untested
[Change Password-26] |  | _ The user successfully sign-in into the system. Hover over the "User Name" label or icon → open the "Thông tin của tôi" dropdown → select the "Đổi Mật Khẩu" form. | Fill in all three password fields: +Mật khẩu cũ: +Mẩu khẩu mới: Abcd@123 +Xác nhận lại mật khẩu: Abcd@123 _ Pressing the button "Đổi Mật Khẩu". | _ Label "Vui lòng nhập..." will appear on "Mật khẩu cũ". _ Change password attempt was not completed. | Untested

## TC-Search Items
Item Test | Search Items
Test requirement | Google Chrome Web Browser , Chrome DevTools
Tester | Hoàng Đỉnh
Pass | Fail | NT | N/A | Number of Test cases
6 | 1 | 10 | 1 | 18
% | % | % | %
ID | Test Case Description | Pre-condition | Test Case Procedure | Expected Output | Result | Test date | Tester | Note
1. UI Testing
[Search Items-1] | _ Verify UI of Search Items | _ Visit the URL: Moriitalia.com | _ Reach the page successfully. | _ The Search Items interface wil present the following fields: + Textbox + Icon Search | Pass |  | Hoàng Đỉnh
[Search Items-2] | _ Verify Textbox | _ Visit the URL: Moriitalia.com | _ Reach the page successfully. | _ System will display blank Textbox with placeholder "Tìm theo tên sản phẩm, thương hiệu" by default. _ Allow users to enter a minimum of 2 characters in textbox. _ The placeholder will automatically disappear when the user starts typing. | Fail
[Search Items-3] | _ Verify Icon Search | _ Visit the URL: Moriitalia.com | _ Reach the page successfully. | _ Search icon will show in textbox and align right. _ Verify that all icon area are clickable. _ Allow user press to search items. _ Hovering over the search icon will appear the cursor. | N/A
2. Functional Testing
[Search Items-4] | _ Check Search Functional | _ Visit the URL: Moriitalia.com | _ Input keyword "Nồi cơm" into the Search field. | _ System will display a dropdown list of “Nồi cơm” product suggestions while the user is typing.
[Search Items-5] |  | _ Visit the URL: Moriitalia.com | _ Input keyword "Chảo" into the Search field. _ Pressing the "Enter" on the keyboard | _ Redirect to the Search Results page and display all “Chảo” products. | Pass
[Search Items-6] |  | _ Visit the URL: Moriitalia.com | _ Input keyword "Chảo" into the Search field. _ Click on the icon Search. | _ Redirect to the Search Results page and display all “Chảo” products. | Pass
[Search Items-7] |  | _ Visit the URL: Moriitalia.com | _ Copy keyword "Chảo" from the other source. _ Right click mouse - > paste. | _ Allow user paste keywords using the mouse. | Pass
[Search Items-8] |  | _ Visit the URL: Moriitalia.com | _ Input keyword "a" into the Search field. _ Click on the icon Search. | _ Error message will display "Tìm kiếm với chiều dài tối thiểu 2 ký tự". _ Search items was not completed. | Untested
[Search Items-9] |  | _ Visit the URL: Moriitalia.com | _ Input keyword "aaaaa..." (length 50) into the Search field. _ Click on the icon Search. | _ Error message will display "Tìm kiếm với chiều dài tối đa 20 ký tự". _ Search items was not completed. | Untested
[Search Items-10] |  | _ Visit the URL: Moriitalia.com | _ Input keyword ")))***" into the Search field. _ Click on the icon Search. | _ Error message will display "Từ khóa tìm kiếm không hợp lệ". _ Search items was not completed. | Pass
[Search Items-11] |  | _ Visit the URL: Moriitalia.com | _ Input keyword "!@#$%&" into the Search field. _ Click on the icon Search. | _ Error message will display "Từ khóa tìm kiếm không hợp lệ". _ Search items was not completed. | Pass
[Search Items-12] |  | _ Visit the URL: Moriitalia.com | _ Leave the Search field blank / empty. _ Click on the icon Search. | _ Error message will display "Vui lòng nhập thông tin tìm kiếm". _ Search items was not completed. | Untested
[Search Items-13] |  | _ Visit the URL: Moriitalia.com | _ Input keyword "Nồi cơm" into the Search field. _ Click on the icon Search. | _ The response time must be within an acceptable threshold < 1 second (Chrome DevTools). _ Redirect to the Search Results page and display all “Chảo” products. | Untested
[Search Items-14] |  | _ Visit the URL: Moriitalia.com | _ Input keyword "Nồi cơm" into the Search field. _ Click on the icon Search. | _ The response time must be within an acceptable threshold < 0.5 second (Chrome DevTools). _ Redirect to the Search Results page and display all “Chảo” products. | Untested
[Search Items-15] |  | _ Visit the URL: Moriitalia.com | _ Input keyword "Bình Giữ Nhiệt" into the Search field. _ Click on the icon Search. | _ Pagination is added when the number of search results exceeds the number of items displayed per page. | Untested
[Search Items-16] |  | _ Visit the URL: Moriitalia.com | _ Input keyword "Bình Giữ Nhiệt" into the Search field. _ Click on the icon Search. _ Tap the page 2 on Pagination. | _ Search results of items page 2 will be displayed. | Untested
[Search Items-17] |  | _ Visit the URL: Moriitalia.com | _ Input keyword "Bình Giữ Nhiệt" into the Search field. _ Click on the icon Search. _ Tap the icon next on Pagination. | _ Search results of items next page will be displayed. | Untested
[Search Items-18] |  | _ Visit the URL: Moriitalia.com | _ Input keyword "Bình Giữ Nhiệt" into the Search field. _ Click on the icon Search. _ Select "Giá tăng dần" by tap the dropdown list "Sắp xếp theo:". | _ Search results will be sorted by ascending price. | Untested
[Search Items-19] |  | _ Visit the URL: Moriitalia.com | _ Input keyword "Bình Giữ Nhiệt" into the Search field. _ Click on the icon Search. _ Select "Giá giảm dần" by tap the dropdown list "Sắp xếp theo:". | _ Search results will be sorted by decending price. | Untested
[Search Items-20] |  | _ Visit the URL: Moriitalia.com | _ Input keyword "Bình Giữ Nhiệt" into the Search field. _ Click on the icon Search. _ Select "Mới nhất" by tap the dropdown list "Sắp xếp theo:". | _ Search results will be sorted by newly items.
[Search Items-21] |  | _ Visit the URL: Moriitalia.com | _ Input keyword "Bình Giữ Nhiệt" into the Search field. _ Click on the icon Search. _ Select "Độ phổ biến" by tap the dropdown list "Sắp xếp theo:". | _ Search results will be sorted by popular items.
[Search Items-22] |  | _ Visit the URL: Moriitalia.com | _ Input keyword "Bình Giữ Nhiệt" into the Search field. _ Click on the icon Search. _ Adjust the price range from 1,000,000 to 2,000,000. on "Giá" section. _ Activate button "TÌM THEO GIÁ". | _All "Bình Giữ Nhiệt" products priced from 1,000,000 to 2,000,000 will be displayed.
[Search Items-23] |  | _ Visit the URL: Moriitalia.com | _ Input keyword "Bình Giữ Nhiệt" into the Search field. _ Click on the icon Search. _ Adjust the price range from 0 to 0 on "Giá" section. _ Activate button "TÌM THEO GIÁ". | _ No results found for "Bình Giữ Nhiệt" products.
[Search Items-24] |  | _ Visit the URL: Moriitalia.com | _ Input keyword "Bình Giữ Nhiệt" into the Search field. _ Click on the icon Search. | _ Products related to "Bình Giữ Nhiệt" will be suggested on the bottom page.

## TC-Product Detail
Item Test | Product Detail
Test requirement | Google Chrome Web Browser
Tester | Hoàng Đỉnh
Pass | Fail | NT | N/A | Number of Test cases
6 | 6 | 1 | 10 | 23
% | % | % | %
ID | Test Case Description | Pre-condition | Test Case Procedure | Expected Output | Result | Test date | Tester | Note
1. UI Testing
[Product Detail-1] | _Verify UI of Product Detail | _Visit the URL: Morritalia.com _Input keyword "Bình Giữ Nhiệt" into the Search field and tap search. _ Click on the first result "Bình Giữ Nhiệt" product. | _ Reach product detail page successfully. | _ The Product detail interface wil present the following fields: + Navigation Path. + Main Product Image + Product image gallery + Product brand, name, code. + Product description. + Star rating + Feedback + Price + Purchase Interaction. + Policy & Support + Suggestion. | Pass |  | Hoàng Đỉnh
[Product Detail-2] | _Verify Navigation Path | _Visit the URL: Morritalia.com _Input keyword "Bình Giữ Nhiệt" into the Search field and tap search. _ Click on the first result "Bình Giữ Nhiệt" product. | _ Reach product detail page successfully. | _ System will show navigation path " /ĐỒ DÙNG DÃ NGOẠI/Bình giữ nhiệt" _ Allow user access each category by select on path.
[Product Detail-3] | _Verify main product image. | _Visit the URL: Morritalia.com _Input keyword "Bình Giữ Nhiệt" into the Search field and tap search. _ Click on the first result "Bình Giữ Nhiệt" product. | _ Reach product detail page successfully. | _ Main product image will appear clearly image with no blur or pixelated. _ Hover over the image will zoom in smoothly with no lag. _ Image can clickable allow user access to product detailed.
[Product Detail-4] | _Verify product image gallery. | _Visit the URL: Morritalia.com _Input keyword "Bình Giữ Nhiệt" into the Search field and tap search. _ Click on the first result "Bình Giữ Nhiệt" product. | _ Reach product detail page successfully. | _ First image will be selected by default. _ All image is sharp, properly sized not blur or broken. _ Main image update by selected thumbnail.
[Product Detail-5] | _Verify product brand, name, code. | _Visit the URL: Morritalia.com _Input keyword "Bình Giữ Nhiệt" into the Search field and tap search. _ Click on the first result "Bình Giữ Nhiệt" product. | _ Reach product detail page successfully. | _ Product brand, name, code is visible and matches the item. _ No font issues or spelling errors.
[Product Detail-6] | _Verify Product description. | _Visit the URL: Morritalia.com _Input keyword "Bình Giữ Nhiệt" into the Search field and tap search. _ Click on the first result "Bình Giữ Nhiệt" product. | _ Reach product detail page successfully. | _ Product description will display: + Detailed description: materials, dimensions, usage. + Technical specifications: capacity, weight, thermal retention. + Usage or care instructions.
[Product Detail-7] | _Verify Star rating. | _Visit the URL: Morritalia.com _Input keyword "Bình Giữ Nhiệt" into the Search field and tap search. _ Click on the first result "Bình Giữ Nhiệt" product. | _ Reach product detail page successfully. | _ Star rating will display average point by the default. _ Allow user click on to access user review. | Fail
[Product Detail-8] | _Verify Feedback | _Visit the URL: Morritalia.com _Input keyword "Bình Giữ Nhiệt" into the Search field and tap search. _ Click on the first result "Bình Giữ Nhiệt" product. | _ Reach product detail page successfully. | _ Feedback will display by default. _ Allow user input data and upload image. _ Have a feature thumbs-up icon for highly rated reviews. | N/A
[Product Detail-9] | _ Verify product price | _Visit the URL: Morritalia.com _Input keyword "Bình Giữ Nhiệt" into the Search field and tap search. _ Click on the first result "Bình Giữ Nhiệt" product. | _ Reach product detail page successfully. | _ Product price is shown accurately. _ Currency format (đ) and thousand separators are correct. | Fail
[Product Detail-10] | _ Verify Purchase Interaction 1 (Quantity selection) | _Visit the URL: Morritalia.com _Input keyword "Bình Giữ Nhiệt" into the Search field and tap search. _ Click on the first result "Bình Giữ Nhiệt" product. | _ Reach product detail page successfully. | _ Quantity selection will display " - [number] + " format by default. _ User can be adjusted quantity via +/- buttons.
[Product Detail-11] | _ Verify Purchase Interaction 2 (Add to cart) | _Visit the URL: Morritalia.com _Input keyword "Bình Giữ Nhiệt" into the Search field and tap search. _ Click on the first result "Bình Giữ Nhiệt" product. | _ Reach product detail page successfully. | _ Button "Thêm Vào Giỏ Hàng" will show on page. _ Verify that all button area are clickable, not only text. _ Allow user press to add cart. _ Hovering over the button triggers a glowing effect that lights up the button. | Fail
[Product Detail-12] | _ Verify Purchase Interaction 3 (Promotion status) | _Visit the URL: Morritalia.com _Input keyword "Bình Giữ Nhiệt" into the Search field and tap search. _ Click on the first result "Bình Giữ Nhiệt" product. | _ Reach product detail page successfully. | _ original price will show this format and discounted price is highlighted. _ “- number %” appears near the price and product image. _ Remaining promotion time is shown accurately. | N/A
[Product Detail-13] | _ Verify Policy & Support | _Visit the URL: Morritalia.com _Input keyword "Bình Giữ Nhiệt" into the Search field and tap search. _ Click on the first result "Bình Giữ Nhiệt" product. | _ Reach product detail page successfully. | _ System will display "Phí ship 0đ" under price label by default. _ Label "Trả hàng hoàn tiền miễn phí trong vòng 7 ngày." will appear under product name. _ "Bảo hành + number + năm cho các sản phẩm thuộc danh mục" format will show (if applicable) on product. | N/A
[Product Detail-14] | _ Verify Suggestion. | _Visit the URL: Morritalia.com _Input keyword "Bình Giữ Nhiệt" into the Search field and tap search. _ Click on the first result "Bình Giữ Nhiệt" product. | _ Reach product detail page successfully. | _ System will display "Sản phẩm thường mua kèm" under description by default. _ Product image show clearly image with no blur or broken. _ Can navigate button to check previous and next product. _ Allow user click to see product detail. | N/A
2. Functional Testing
[Product Detail-15] | _Verify Product Detail Testing | _Visit the URL: Morritalia.com _ The user successfully sign-in into the system. _Search and select "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" _ Click on the result product to go product detail. | _ Press the button "Mua Ngay". | _ Message "Sản phẩm đã được thêm vào giỏ hàng của bạn." will appear on top page. _ Allow user click on link "giỏ hàng của bạn" to access cart page. _ Can hide message by tap x icon. _ Cart icon will update 1. | Pass
[Product Detail-16] |  | _Visit the URL: Morritalia.com _ The user successfully sign-in into the system. _Search and select "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" _ Click on the result product to go product detail. | _ Increase the quantity of the product by 10 using the '+' button. _ Press the button "Mua Ngay". | _ Message "Sản phẩm đã được thêm vào giỏ hàng của bạn." will appear on top page. _ Allow user click on link "giỏ hàng của bạn" to access cart page. _ Can hide message by tap x icon. _ Cart icon will update 10. | Pass
[Product Detail-17] |  | _Visit the URL: Morritalia.com _ The user not sign-in into the system. _Search and select "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" _ Click on the result product to go product detail. | _ Press the button "Mua Ngay". | _ Error message "Vui lòng đăng nhập để thêm sản phẩm vào giỏ hàng" will appear. _ Attemp add to cart product fail. | Fail
[Product Detail-18] |  | _Visit the URL: Morritalia.com _ The user successfully sign-in into the system. _Search and select "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" _ Click on the result product to go product detail. | _ Increase the quantity of the product by 50 using the '+' button. _ Press the button "Mua Ngay". | _ Warning message "Số lượng đặt hàng quá lớn. Vui lòng liên hệ bộ phận chăm sóc khách hàng để được hỗ trợ." will appear on top page. _ Attemp add to cart product fail. | Fail
[Product Detail-19] |  | _Visit the URL: Morritalia.com _ The user successfully sign-in into the system. _Search and select "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" _ Click on the result product to go product detail. | _ Increase the quantity of the product by 5 to 10 using the '+' button. | _ From the 5th product, the system will display the remaining stock quantity by format "Còn lại - number - sản phẩm". _ Each time the '+' button is pressed, the stock number will automatically decrease. | Fail
[Product Detail-20] |  | _Visit the URL: Morritalia.com _ The user successfully sign-in into the system. _Search and select "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" _ Click on the result product to go product detail. | _ Increase the quantity of the product by 1 to 5 using the '+' button. _ Press the - button to decrease until quantity of the product to 1. _ Continue press - button to decrease. | _ The quantity will be fixed at a minimum of 1 product. _ Users cannot select a negative number ( <0 ) of quantity. | Pass
[Product Detail-21] |  | _Visit the URL: Morritalia.com _ The user successfully sign-in into the system. _Search and select "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" _ Click on the result product to go product detail. | _ Increase the quantity of the product by 5 using the '+' button. | _ Total price wil be automatically updated by format " Price = unit price × 5". | Pass
[Product Detail-22] |  | _Visit the URL: Morritalia.com _ The user successfully sign-in into the system. | _ Simulate accessing a discontinued product URL: https://moriitalia.com/binh-giu-nhiet-travel-la-fonte-inox-304-co-quai-xach-tien-loi-470ml-010245-blu-discontinued. | _ System will show title "Không Tìm Thấy Trang". _ Message "Oops, trang này hiện không tồn tại, vui lòng quay về Trang chủ." _ Page automatically reload to homepage. | Untested
[Product Detail-23] |  | _Visit the URL: Morritalia.com _ The user successfully sign-in into the system. _Search and select "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" _ Click on the result product to go product detail. | _ Activate dropdown list "Đánh giá sản phẩm" on page. _ Select "Sắp xếp theo bình luận mới nhất" . | _ User review will be sorted by lastest. | N/A
[Product Detail-24] |  | _Visit the URL: Morritalia.com _ The user successfully sign-in into the system. _Search and select "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" _ Click on the result product to go product detail. | _ Activate dropdown list "Đánh giá sản phẩm" on page. _ Select "Sắp xếp theo bình luận cũ nhất" . | _ User review will be sorted by oldest. | N/A
[Product Detail-25] |  | _Visit the URL: Morritalia.com _ The user successfully sign-in into the system. _Search and select "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" _ Click on the result product to go product detail. | _ Activate dropdown list "Đánh giá sản phẩm" on page. _ Select "Sắp xếp theo bình luận hữa ích" . | _ User review will be sorted by most heplful. | N/A
[Product Detail-26] |  | _Visit the URL: Morritalia.com _ The user successfully sign-in into the system. _ User already bought 1 "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" product. _ Go to go product detail. | _ Select the 1-star rating. _ Leave the comment box empty. _ Click the "Gửi" button to submit. | _ The system will display users' 1-star reviews with no comment. | N/A
[Product Detail-27] |  | _Visit the URL: Morritalia.com _ The user successfully sign-in into the system. _ User already bought 1 "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" product. _ Go to go product detail. | _ Select the 5-star rating. _ Leave the comment box empty. _ Click the "Gửi" button to submit. | _ The system will display users' 5-star reviews with no comment. | Pass
[Product Detail-28] |  | _Visit the URL: Morritalia.com _ The user successfully sign-in into the system. _ User already bought 1 "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" product. _ Go to go product detail. | _ Select the 1-star rating. _ Typing "Sản phẩm có thiết kế nhỏ gọn, bền bỉ và chống được va đập " in the comment box. _ Click the "Gửi" button to submit. | _ The system will display users' 1-star reviews with comment "Sản phẩm có thiết kế nhỏ gọn, bền bỉ và chống được va đập." | N/A
[Product Detail-29] |  | _Visit the URL: Morritalia.com _ The user successfully sign-in into the system. _ User already bought 1 "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" product. _ Go to go product detail. | _ Select the 5-star rating. _ Typing "Sản phẩm có thiết kế nhỏ gọn, bền bỉ và chống được va đập " in the comment box. _ Click the "Gửi" button to submit. | _ The system will display users' 5-star reviews with comment "Sản phẩm có thiết kế nhỏ gọn, bền bỉ và chống được va đập." | N/A

## TC-Shopping Cart
Item Test | Shopping Cart
Test requirement | Google Chrome Web Browser
Tester | Hoàng Đỉnh
Pass | Fail | NT | N/A | Number of Test cases
19 | 6 | 7 | 1 | 33
% | % | % | %
ID | Test Case Description | Pre-condition | Test Case Procedure | Expected Output | Result | Test date | Tester | Note
1.1 UI Testing Cart Icon
[Shopping Cart-1] | _Verify UI of Cart Icon. | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. | _ Hovering over and select the Cart icon. | _ The Cart icon interface wil present the following fields: + Title "Giỏ Hàng" + Link "Sản Phẩm" + Product Image + Product name, price, quantity. + Button "ĐẾN GIỎ HÀNG" | Pass |  | Hoàng Đỉnh
[Shopping Cart-2] | _Verify Title "Giỏ Hàng" | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. | _ Hovering over and select the Cart icon. | _ System will display title "Giỏ Hàng". _ The title should not be cut off, overflow, and align left. | Fail
[Shopping Cart-3] | _Verify Link "Sản Phẩm" | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. | _ Hovering over and select the Cart icon. | _ Link "Sản Phẩm(number)" will display on page and show correct total product in cart by default. _ Hovering over link will trigger a glowing effect. _ User able to click link will redirect to Cart page. | Fail
[Shopping Cart-4] | _Verify Product Image | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. | _ Hovering over and select the Cart icon. | _ Product image is fully visible, not broken or missing. _ Image is clear, not blurry or pixelated, align left. _ Allow user access Product detail by click on image. | N/A
[Shopping Cart-5] | _Verify product name, price, quatity. | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. | _ Hovering over and select the Cart icon. | _ Display product name, price, quantity by default. _ Product name, price, quantity are same as product in cart , without spelling errors. | Pass
[Shopping Cart-6] | _Button "Đến giỏ hàng" | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. | _ Hovering over and select the Cart icon. | _ Button "Đến Giỏ Hàng" will show on page. _ Verify that all button area are clickable, not only text. _ Allow user press to access Cart page. _ Hovering over the button triggers a glowing effect that lights up the button. | Pass
1.2 UI Testing Cart Page
[Shopping Cart-7] | _Verify UI of Cart Page | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. | _ Hovering over and select the Cart icon. _ Press the button "Đến Giỏ Hàng". | _ The Cart page interface wil present the following fields: + Product display + Cart sumary + Functional Button + Discount & Gift + Shipping fee estimation | Pass
[Shopping Cart-8] | _ Verify Product display (1) | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. | _ Add any product on product detail page. _ Hovering over and select the Cart icon. _ Press the button "Đến Giỏ Hàng". | _ Product name is displayed correctly. _ Product image is visible and matches the item. | Pass
[Shopping Cart-9] | _ Verify Product display (2) | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. | _ Add any product on product detail page. _ Hovering over and select the Cart icon. _ Press the button "Đến Giỏ Hàng". | _ Unit price is shown accurately. _ Quantity can be adjusted via +/- buttons. _ Total price per item = unit price × quantity. | Pass
[Shopping Cart-10] | _ Verify Cart sumary (1) | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. | _ Add any product on product detail page. _ Hovering over and select the Cart icon. _ Press the button "Đến Giỏ Hàng". | _ "Thành tiền", "Tạm tính" are visible and calculated correctly. _ Currency format (đ) and thousand separators are correct. | Pass
[Shopping Cart-11] | _ Verify Cart sumary (2) | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. | _ Add any product on product detail page. _ Hovering over and select the Cart icon. _ Press the button "Đến Giỏ Hàng". | _ Total number of selected items is displayed on the page. | Fail
[Shopping Cart-12] | _ Verify Functional Button "Tiến Hành Đặt Hàng" | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. | _ Add any product on product detail page. _ Hovering over and select the Cart icon. _ Press the button "Đến Giỏ Hàng". | _ Button "Tiến Hành Đặt Hàng" will show on page. _ Verify that all button area are clickable, not only text. _ Allow user press to check out. _ Hovering over the button triggers a glowing effect that lights up the button. | Pass
[Shopping Cart-13] | _ Verify Functional Button Remove Items | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. | _ Add any product on product detail page. _ Hovering over and select the Cart icon. _ Press the button "Đến Giỏ Hàng". | _ Button Remove Item will show on page. _ Verify that all button area are clickable. _ Allow user press to remove product. | Pass
[Shopping Cart-14] | _ Verify Discount | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. | _ Add any product on product detail page. _ Hovering over and select the Cart icon. _ Press the button "Đến Giỏ Hàng". | _ System will display blank Textbox with placeholder "Nhập Mã Giảm Giá" by default. _ Allow users to enter valid data in textbox. _ The placeholder will automatically disappear when the user starts typing. | Pass
[Shopping Cart-15] | _ Verify Gift | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. | _ Add any product on product detail page. _ Hovering over and select the Cart icon. _ Press the button "Đến Giỏ Hàng". | _ System will show blank textbox "Thẻ Quà Tặng" by default. _ Allow users to enter valid data in textbox. | Pass
[Shopping Cart-16] | _ Verify Shipping fee estimated | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. | _ Add any product on product detail page. _ Hovering over and select the Cart icon. _ Press the button "Đến Giỏ Hàng". | _ Shipping fee estimated form will display on page. _ Allow user can select "Tỉnh/Thành", "Quận/Huyện" on dropdown box. _ Allow user can clickable button "Tính Phí". _ "Shipping Method (estimated price)" will display after user select address and activate button "Tính Phí". | Pass
2. Functional Testing
[Shopping Cart-17] | _ Check Cart button Functional | _ Visit the URL: Moriitalia.com. | _ Reach the page successfully. | _ Cart button will blank / hide by default. | Pass
[Shopping Cart-18] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. | _ User logon account was completed. | _ Cart button will show "0" product on icon by default. | Pass
[Shopping Cart-19] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. | _ Search and select product "Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359". _ +1 the product on product detail page. _ Press the button "Mua Ngay". | _ Cart button will show "1" product on icon by default. | Pass
[Shopping Cart-20] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. | _ Search and select product "Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359". _ +1 the product on product detail page. _ Press the button "Mua Ngay". _ Go to homepage. _ Search and select product "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU". _ +1 the product on product detail page. _ Press the button "Mua Ngay". | _ Cart button will show "2" product on icon by default. | Pass
[Shopping Cart-21] | _ Check Cart Page Functional | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. | _ Search and select product "Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359". _ +1 the product on product detail page. _ Press the button "Mua Ngay". _ Hovering over and select the Cart icon. _ Press the button "Đến Giỏ Hàng". | _ Product "Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359" will show 1 on cart page. | Pass
[Shopping Cart-22] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ Already + 1 product "Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359" in cart. | _ Search and select product "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU". _ +1 the product on product detail page. _ Press the button "Mua Ngay". _ Hovering over and select the Cart icon. _ Press the button "Đến Giỏ Hàng". | _ Product "Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359" will show 1 on cart page. _ Product ""Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" will show 1 on cart page. _ "Thành tiên" will show total price of two items. | Pass
|  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ Already + 1 product "Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359" in cart. | _ Search and select product "Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359". _ +1 the product on product detail page. _ Press the button "Mua Ngay". _ Hovering over and select the Cart icon. _ Press the button "Đến Giỏ Hàng". | _ Product "Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359" will show 2 on cart page. _ "Thành tiên" will show total price of two items.
[Shopping Cart-24] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. | _ Search and select product "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU". _ Hovering over product image and click "Mua Ngay". _ Hovering over and select the Cart icon. _ Press the button "Đến Giỏ Hàng". _ Press + button 4 times. _ Press the button "Cập Nhật Giỏ Hàng" | _ Product "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" will show 5 on cart page. _ Total price per item = unit price × 5. _ "Thành tiên" will update total price of 5 items. | Untested
[Shopping Cart-25] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ Already + 5 product "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" in cart. | _ Hovering over and select the Cart icon. _ Press the button "Đến Giỏ Hàng". _ Press - button 3 times. _ Press the button "Cập Nhật Giỏ Hàng" | _ Product "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" will show 2 on cart page. _ Total price per item = unit price × 2. _ "Thành tiên" will update total price of 2 items. | Untested
[Shopping Cart-26] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ Already +1 product "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" in cart. | _ Hovering over and select the Cart icon. _ Press the button "Đến Giỏ Hàng". _ Press remove items button. _ Press the button "Cập Nhật Giỏ Hàng" | _ System will reload and items successfully remove from cart page. _ "Thành tiên" will update total price. | Untested
[Shopping Cart-27] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ Already +1 product "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" in cart. | _ Hovering over and select the Cart icon. _ Press the button "Đến Giỏ Hàng". _ Enter a valid (active) discount code into the textbox "Nhập mã giảm giá". _ Press the button "Áp Dụng". | _ Message "Mã giảm giá được được áp thành công". _ "Thành tiền" will be reduced when a discount code is applied. | Untested
[Shopping Cart-28] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ Already +1 product "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" in cart. | _ Hovering over and select the Cart icon. _ Press the button "Đến Giỏ Hàng". _ Enter a invalid discount code ("!@#$%^&") into the textbox "Nhập mã giảm giá". _ Press the button "Áp Dụng". | _ Message "Mã giảm giá không hợp lệ hoặc đã hết hạn sử dụng.". _ Attemp apply discount code was not completed. | Pass
[Shopping Cart-29] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ Already +1 product "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" in cart. | _ Hovering over and select the Cart icon. _ Press the button "Đến Giỏ Hàng". _ Enter a expired discount code into the textbox "Nhập mã giảm giá". _ Press the button "Áp Dụng". | _ Message "Mã giảm giá không hợp lệ hoặc đã hết hạn sử dụng.". _ Attemp apply discount code was not completed. | Untested
[Shopping Cart-30] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ Already +1 product "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" in cart. | _ Hovering over and select the Cart icon. _ Press the button "Đến Giỏ Hàng". _ Enter a valid (active) gift code into the textbox "Thẻ Quà Tặng" _ Press the button "Áp Dụng". | _ Message "Thẻ quà tặng được áp thành công". _ "Thành tiền" will be reduced when a discount code is applied. | Untested
[Shopping Cart-31] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ Already +1 product "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" in cart. | _ Hovering over and select the Cart icon. _ Press the button "Đến Giỏ Hàng". _ Enter a invalid gift code (****$$$$) into the textbox "Thẻ Quà Tặng" _ Press the button "Áp Dụng". | _ Message "Thẻ quà tặng không hợp lệ". _ Attemp apply gift code was not completed. | Fail |  |  | _ Wrong error message.
[Shopping Cart-32] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ Already +1 product "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" in cart. | _ Hovering over and select the Cart icon. _ Press the button "Đến Giỏ Hàng". _ Enter a expired gift code into the textbox "Thẻ Quà Tặng" _ Press the button "Áp Dụng". | _ Message "Thẻ quà tặng không hợp lệ". _ Attemp apply gift code was not completed. | Untested
[Shopping Cart-33] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ Already +1 product "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" in cart. | _ Hovering over and select the Cart icon. _ Press the button "Đến Giỏ Hàng". _ Tap dropdown box "Ước tính phí giao hàng". _ Select "Tp. Hồ Chí Minh" on "Tỉnh / Thành". _ Select "Quận 7" on "Quận / Huyện". _ Activate button "Tính Phí". | _ System will show message "Giao hàng tiêu chuẩn ( 30.000 đ)". | Fail |  |  | _ Not show shipping fee.
[Shopping Cart-34] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ Already +1 product "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" in cart. | _ Hovering over and select the Cart icon. _ Press the button "Đến Giỏ Hàng". _ Press + button 5 times. _ Press the button "Cập Nhật Giỏ Hàng" _ Tap dropdown box "Ước tính phí giao hàng". _ Select "Tp. Hồ Chí Minh" on "Tỉnh / Thành". _ Select "Quận 7" on "Quận / Huyện". _ Activate button "Tính Phí". | _ System will show message "Giao hàng tiêu chuẩn (> 30.000 đ)". | Fail |  |  | _ Not show shipping fee.

## TC-Payment
Item Test | Payment
Test requirement | Google Chrome Web Browser
Tester | Hoàng Đỉnh
Pass | Fail | NT | N/A | Number of Test cases
0 | 0 | 0 | 0 | 0
% | % | % | %
ID | Test Case Description | Pre-condition | Test Case Procedure | Expected Output | Result | Test date | Tester | Note
1.1.
1.2.

## TC-Order Manage
Item Test | Order Manage
Test requirement | Google Chrome Web Browser
Tester | Hoàng Đỉnh
Pass | Fail | NT | N/A | Number of Test cases
7 | 2 | 5 | 16 | 30
% | % | % | %
ID | Test Case Description | Pre-condition | Test Case Procedure | Expected Output | Result | Test date | Tester | Note
1.1 UI Testing Order Manage
[Order Manage-1] | _Verify UI of Order Manage. | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". | _ Mouse hover on "User Name" label or icon. _ Click on the dropdown link "Đơn Hàng Của Tôi". | _ The Order Manage interface wil present the following fields: + Title "Đơn Hàng Của Tôi" + Order code. + Search Order. + Order status. + Order product Image + Ordered product name, price, quantity, policy. + Order detaild link. + Delivery time estimate. + Total ordered price. + Button "Hủy Bỏ". | Fail |  | Hoàng Đỉnh
[Order Manage-2] | _ Verify Title "Đơn Hàng Của Tôi" | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". | _ Mouse hover on "User Name" label or icon. _ Click on the dropdown link "Đơn Hàng Của Tôi". | _ System will display title "Đơn Hàng Của Tôi". _ The title should not be cut off, overflow, and align left. | Pass
[Order Manage-3] | _ Verify Order code. | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". | _ Mouse hover on "User Name" label or icon. _ Click on the dropdown link "Đơn Hàng Của Tôi". | _ System will display product code with format "MO-dd/mm/yy-order number". | Pass
[Order Manage-4] | _ Verify Search Order | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". | _ Mouse hover on "User Name" label or icon. _ Click on the dropdown link "Đơn Hàng Của Tôi". | _ Search icon will show in textbox and align right and all icon area are clickable. _ System will display blank Textbox with placeholder "Tìm theo tên sản phẩm, mã đơn hàng" by default. _ The placeholder will automatically disappear when the user starts typing. _ Hovering over the search icon will appear the cursor. _ Allow user press to search items. | Pass
[Order Manage-5] | _ Verify Order status. | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". | _ Mouse hover on "User Name" label or icon. _ Click on the dropdown link "Đơn Hàng Của Tôi". | _ System will display order status. | Pass
[Order Manage-6] | _ Verify Order product image. | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". | _ Mouse hover on "User Name" label or icon. _ Click on the dropdown link "Đơn Hàng Của Tôi". | _ Product image will appear clearly image with no blur or pixelated. _ Hover over the image will zoom in smoothly with no lag. _ Image can clickable allow user access to product detailed. | N/A
[Order Manage-7] | _ Verify Ordered product name, price, quantity, policy. | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". | _ Mouse hover on "User Name" label or icon. _ Click on the dropdown link "Đơn Hàng Của Tôi". | _ Product name, price, quantity, policy are visible and matches the item. _ No font issues or spelling errors. | Pass
[Order Manage-8] | _ Verify Order Detailed link. | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". | _ Mouse hover on "User Name" label or icon. _ Click on the dropdown link "Đơn Hàng Của Tôi". | _ Forgot Password Link "Xem chi tiết" will display on page by default. _ Hovering over link will trigger a glowing effect. _ User able to click link will redirect to order detailed page. | Fail
[Order Manage-9] | _ Delivery time estimate. | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". | _ Mouse hover on "User Name" label or icon. _ Click on the dropdown link "Đơn Hàng Của Tôi". | _ System will show delivery time estimate follwing format "Dự Kiến Giao dd/mm - dd/mm". _ Allow user click to access detail order page. | N/A
[Order Manage-10] | _ Verify total ordered price. | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". | _ Mouse hover on "User Name" label or icon. _ Click on the dropdown link "Đơn Hàng Của Tôi". | _ System will show delivery time estimate follwing format "Tổng cộng ( 'number' Sản phẩm): 'price' đ". _ Total price per item = (unit price × quantity) + shipping fee. _ Currency format (đ) and thousand separators are correct. _ Allow user click to access detail order page. | N/A
[Order Manage-11] | _ Verify button "Hủy Bỏ". | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". | _ Mouse hover on "User Name" label or icon. _ Click on the dropdown link "Đơn Hàng Của Tôi". | _ Button "Hủy Bỏ" will show on page. _ Verify that all button area are clickable, not only text. _ Allow user press to canceled order. _ Hovering over the button triggers a glowing effect that lights up the button. | N/A
1.2. UI Testing Order Detailed
[Order Manage-12] | _Verify UI of Order Detailed link. | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". | _ Mouse hover on "User Name" label or icon. _ Click on the dropdown link "Đơn Hàng Của Tôi". _ Press the order detailed link. | _ The Order Manage interface wil present the following fields: + Order code. + Order status. + Order product Image + Ordered product name, price, quantity, policy. + Delivery time estimate. + Total ordered price. + Button "Hủy Bỏ". | N/A
2. Functional Testing
[Order Manage-13] | _ Check Order manage Functional | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". | _ Search and select product "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU". _ Complete the purchase the product. | _ System will display 2 product "Nồi cơm điện…", "Bình giữ nhiệt…" on Order manage page. | Pass
[Order Manage-14] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. | _ User was not purchased any product. | _ Order manage will leave empty. | Pass
[Order Manage-15] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". | _ Required admin permision: Set order status "Chờ thanh toán". _ Activate button "Hủy". | _ System will show message "Bạn có chắc hủy đơn hàng" with button "Xác Nhận". _ Click button allow user canceled order. _ Click back icon "Hủy Yêu Cầu" will return to order manage page. | N/A
[Order Manage-16] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". | _ Required admin permision: Set order status "Chờ thanh toán". _ Activate button "Hủy". | _ A canceled email will be sent to user address. _ The email will be sending to the inbox folder, not the spam folder. _ Mail subject will start with "Moriitalia - Thông báo đơn hàng … đã bị hủy". _ Email content are in the correct format.
[Order Manage-17] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". | _ Required admin permision: Set order status "Chờ thanh toán". _ No payment is made, (test) waiting 24 hour. | _ Order status will be automatically updated to canceled. _ Button "Hủy" will be replaced by button "Mua Lại".
[Order Manage-18] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". | _ Required admin permision: Set order status "Đã thanh toán, chờ vận chuyển". _ Activate button "Hủy". | _ System will show message "Bạn có chắc hủy đơn hàng, số tiền đã thanh toán sẽ được hoàn trả vào tài khoản…" with button "Xác Nhận". _ Click button allow user canceled order. _ Click back icon "Hủy Yêu Cầu" will return to order manage page. | N/A
[Order Manage-19] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". | _ Required admin permision: Set order status "Đã thanh toán, chờ vận chuyển" with applied discount voucher. _ Activate button "Hủy". | _ System will show message "Bạn có chắc hủy đơn hàng, số tiền đã thanh toán sẽ được hoàn trả vào tài khoản…" with button "Xác Nhận". _ Label "Nếu hủy đơn, bạn có thể bỏ lỡ mã giảm giá" and discount price will show. _ Click button allow user canceled order. _ Click back icon "Hủy Yêu Cầu" will return to order manage page. | N/A
[Order Manage-20] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". | _ Required admin permision: Set order status "Đã vận chuyển" _ Activate button "Hủy". | _ Button "Hủy" will be disabled, user cannot click to canceled order. | N/A
[Order Manage-21] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". | _ Required admin permision: Set order status "Chờ giao hàng" _ Activate button "Hủy". | _ Button "Hủy" will be disabled, user cannot click to canceled order. | N/A
[Order Manage-22] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". | _ Required admin permision: Set order status "Đã giao hàng" _ Activate button "Đánh giá đơn hàng" | _ Button "Hủy" will be replaced by button "Đánh giá đơn hàng." _ Allow user review product on product detail. | N/A
[Order Manage-23] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". | _ Required admin permision: Set order status "Đã giao hàng" _ Activate button "Trả Hoàn / Hoàn Tiền". | _ "Trả Hoàn / Hoàn Tiền" section will pop-up allow user input reason : image, video, text to textbox. _ Click on button "Xác nhận" will send a request to return process. | N/A
[Order Manage-24] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". | _ Input keyword "Nồi Cơm Điện" into the Search field. _ Pressing the "Enter" on the keyboard | _ System will display a list of “Nồi cơm” order suggestions while the user is typing. _ Allow user click to access order detaild. | N/A
[Order Manage-25] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". _ User already purchased product "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" | _ Input keyword "Nồi Cơm Điện" into the Search field. _ Pressing the "Enter" on the keyboard | _ System will display a list of “Nồi cơm” order suggestions while the user is typing. _ Allow user click to access order detaild. | Untested
[Order Manage-26] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". _ User already purchased product "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" | _ Input keyword "Bình giữ nhiệt" into the Search field. _ Pressing the "Enter" on the keyboard | _ System will display a list of “Bình Giữ Nhiệt” order suggestions while the user is typing. _ Allow user click to access order detaild. | Untested
[Order Manage-27] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". _ User already purchased product "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" | _ Input "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" order code into the Search field. _ Pressing the "Enter" on the keyboard | _ System will display a list of “Bình Giữ Nhiệt” order suggestions while the user is typing. _ Allow user click to access order detaild. | Untested
[Order Manage-28] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". _ User already purchased product "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" | _ Leave the search field blank. _ Pressing the "Enter" on the keyboard | _ The system will not respond, and no orders will be displayed. | Untested
[Order Manage-29] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ The product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359" has been completed. _ The product "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" has been completed. | _ Press the link "Lịch Sử Mua Hàng" | _ System will display a list of order completed (2 product). _ Allow user click to access order detaild. | N/A
[Order Manage-30] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ The product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359" has been canceled. _ The product "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" has has been canceled. | _ Press the link "Lịch Sử Mua Hàng" | _ System will display a list of order canceled (2 product). _ Allow user click to access order detaild. | N/A
[Order Manage-31] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". _ User already purchased product "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" | _ Required admin permision: Set order status "Chờ thanh toán" on product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359". Set order status "Đã thanh toán" on product "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" _ Tap the dropdown list "Sắp xếp theo" > select "Trạng thái đơn hàng" > select "Chờ thanh toán". | _ Only order ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359" will show. | N/A
[Order Manage-32] |  | _ Visit the URL: Moriitalia.com. _ The user successfully sign-in into the system. _ User already purchased product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359".". _ User already purchased product "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" | _ Required admin permision: Set order day "11/10/2025" on product ""Nồi Cơm Điện Kuchenzimmer 8in1 Cao Tần (IH) 4L-014359". Set order day "15/10/2025" on product "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" _ Tap the dropdown list "Sắp xếp theo" > select "Thời Gian Đặt Hàng" > select "Ngày Mới Nhât". | _ Only order "Bình giữ nhiệt 2 lớp Inox 304 Basic Pastel La Fonte 750ml-015899-BLU" will show. | Untested

## Permisison Matrix
Module Code
Test requirement
Tester
Pass | Fail | Untested | N/A | Number of Test cases
% | % | % | % | %
No | Function List | Manager | Employee | Director | Internship | Admin | Result | Test date | Tester | Note
Common Role
1 |  | Y* | N | Y* | N | Y*
2 |  | Y* | N | Y* | N | Y*
3 |  | Y* | N | Y* | N | Y*
4 |  | Y* | N | Y* | N | Y*
5 |  | Y |  | Y |  | Y
Others
12 |  | Y* | N | Y* | N | Y*
13 |  | Y* | N | Y* | N | Y*
14 |  | Y* | Y* | Y* | Y* | Y*
15 |  | Y* | Y* | Y* | Y* | Y*
16 |  | Y* | Y* | Y* | Y* | Y*
Note on I8: ====== ID#AAAAcB7S7jU My PC (2022-07-27 11:15:31) Định dang dd/mm/yyy